## Review Info
Peer Review | Metadata | Reviewer Name | Review Time (Hours)
*Work Product Name: | Peer Review #1 | Ravindu | 1.5
*Work Product Size: | 12 files: 6 HTML, 5 CSS, 1 JS
Review Start Date: | 2022-11-21
Review Due Date: | 2022-11-23
Defect Disposition Meeting Date:
Review Completion Date: | 2022-11-23
|  | Total (Hrs) | 1.5
Reviewed work product, and no defects were found

## Review Log
Item# | Reviewer Name | Code Module | Line number | Defect Description or Comment | Major or Minor | Disposition of Defect /Comment | Person Assigned to Resolve | Notes
1 | Ravindu Gunasinghe | Menu |  | Not fully finished yet. Needs to be polished. | Major |  | Ravindu Gunasinghe | Structure is finished and done. Need to add finish touches and add all the menu tabs.
2 | Ravindu Gunasinghe | Account |  | Code is not responisve and the code needs to be organized. | Major |  | Mohammed | The code is a bit scattered therefore, must be organized. Must be forther reviewed any order to make sure the code functions.
3 | Ravindu Gunasinghe | Terms |  | The code is heavily disorganized and messy. | Major |  | Aaron | Code must be reviewed thorougly and reowrked to be less disorderly.
4 | Ravindu Gunasinghe | Sign in |  | Needs finishing tocuhes | Minor |  | Christian | Code is done well, just needs a bit of trimming and beautifying.
5 | Ravindu Gunasinghe | Sign up |  | Needs finishing tocuhes | Minor |  | Christian | Code is done well, just needs a bit of trimming and beautifying.
6 | Ravindu Gunasinghe | Homepage |  | Width issues when going from mobile to Desktop. | Minor |  | Vincent | The widths must be reworked for a smoother transition.
Note on A1: This is a sequential number that gives a reviewer's comments a unique ID for ease of referencing.
Note on B1: Enter your name.
Note on C1: For documents with multiple pages, enter the page number or numbers for the defect or comment. For example: ii, 12, 4-5
Note on D1: Enter the identifying number or title for the Section, Paragraph, Figure, or Table for which you are entering a defect or comment. For examples: 4.6.2, Stakeholder Plan.
Note on E1: Enter a detailed description of the defect you are identifying or provide your detailed comment. Identify only one defect or comment per row.
Note on F1: This column is automatically populated based on the entry chosen in the Defect/Comment Type column.
Note on G1: This column is used to assign a disposition to the review comment.
Note on H1: This column is used for identifying the person assigned to resolve the defect/comment.
Note on I1: This column is used to record freeform notes about each defect and or its disposition.