## Review Info
Peer Review | Metadata | Reviewer Name | Review Time (Hours)
*Work Product Name: | Peer Review #1 | Vince | 1.5
*Work Product Size: | 12 files: 6 HTML, 5 CSS, 1 JS
Review Start Date: | 2022-11-21
Review Due Date: | 2022-11-23
Defect Disposition Meeting Date:
Review Completion Date: | 2022-11-23
|  | Total (Hrs) | 2
Reviewed work product, and no defects were found

## Review Log
Item# | Reviewer Name | Code Module | Line number | Defect Description or Comment | Major or Minor | Disposition of Defect /Comment | Person Assigned to Resolve | Notes
1 | Vincent Fearing | Homepage |  | Links need to be connect and desktop width needs to be finished. | Minor |  | Vincent Fearing | Looks good but needs finishing touches
2 | Vincent Fearing | Account |  | Needs styling | Major |  | Mohammed | Hasn't been styled yet. Needs work.
3 | Vincent Fearing | Forgot |  | Looks good, needs refinement | Minor |  | Chris | Looks good but needs finishing touches
4 | Vincent Fearing | Sign In |  | Looks good, needs refinement | Minor |  | Chris | Looks good but needs finishing touches
5 | Vincent Fearing | Sign Up |  | Looks good, needs refinement | Minor |  | Chris | Looks good but needs finishing touches
6 | Vincent Fearing | Terms |  | Looks good but code is really messy | Major |  | Aaron | code base is messsy and hard to read
Note on A1: ====== ID#AAAAkXMeCqo Natural SPI (2022-11-24 06:53:19) This is a sequential number that gives a reviewer's comments a unique ID for ease of referencing.
Note on B1: ====== ID#AAAAkXMeCqg Natural SPI (2022-11-24 06:53:19) Enter your name.
Note on C1: ====== ID#AAAAkXMeCqk Natural SPI (2022-11-24 06:53:19) For documents with multiple pages, enter the page number or numbers for the defect or comment. For example: ii, 12, 4-5
Note on D1: ====== ID#AAAAkXPJKRU Natural SPI (2022-11-24 06:53:19) Enter the identifying number or title for the Section, Paragraph, Figure, or Table for which you are entering a defect or comment. For examples: 4.6.2, Stakeholder Plan.
Note on E1: ====== ID#AAAAkXMeCqs Natural SPI (2022-11-24 06:53:19) Enter a detailed description of the defect you are identifying or provide your detailed comment. Identify only one defect or comment per row.
Note on F1: ====== ID#AAAAkXMeCqw Natural SPI (2022-11-24 06:53:19) This column is automatically populated based on the entry chosen in the Defect/Comment Type column.
Note on G1: ====== ID#AAAAkXMeCq0 Natural SPI (2022-11-24 06:53:19) This column is used to assign a disposition to the review comment.
Note on H1: ====== ID#AAAAkXMeCq4 Jitka West (2022-11-24 06:53:19) This column is used for identifying the person assigned to resolve the defect/comment.
Note on I1: ====== ID#AAAAkXMeCq8 Jitka West (2022-11-24 06:53:19) This column is used to record freeform notes about each defect and or its disposition.