## Review Info
Peer Review | Metadata | Reviewer Name | Review Time (Hours)
*Work Product Name: | Peer Review #2 | Aaron | 1
*Work Product Size: | 15 files: 7 HTML, 6 CSS, 2 JS | Cristian | 2
Review Start Date: | 2022-12-18 | Mohammed | 1
Review Due Date: | 2022-12-18 | Ravindu | 1
Defect Disposition Meeting Date: |  | Talha | 1
Review Completion Date: | 2022-12-18 | Vince | 0
|  | Total (Hrs) | 6
Reviewed work product, and no defects were found

## Review Log
Item# | Reviewer Name | Code Module | Line number | Defect Description or Comment | Major or Minor | Disposition of Defect /Comment | Person Assigned to Resolve | Notes
1 | Aaron | checkout.html | page | Remove Quantity, as there might need to be one there. | Minor |  | Talha | Very Minor Task
2 | Aaron | account.html | page | Layout matches theme of website, needs to add more css, Accout Details and Payment details look dull. | Minor |  | Talha
3 | Aaron | account.html | file | Needs to be reworked, not organize. | Minor |  | Cristian
4 | Cristian | terms.html | file | Still need to be organized, looks bery messy. | Minor |  | Cristian and Mohammed
5 | Cristian | cart.html | file | Also needs to be organized | Minor |  | Aaron and Vince
6 | Cristian | index.html | page | Despite Rento being in the bottom right of page, still able to click to the left of it, accessing a link if it was placed in the html file. | Minor |  | Vince and Aaron
7 | Mohammed | Checkout.css | file | Work on css part | Minor |  | Talha
8 | Mohammed | Terms.css | file | Work on css part | Minor |  | Mohammed and Cristian
9 | Mohammed | Terms.html | file | Organize lines of code. | Minor |  | Mohammed and Cristian
10 | Ravindu Gunasinghe | Account.html | webpage | Looks better, but still needs to be polished. | Minor |  | Cristian and Talha
11 | Ravindu Gunasinghe | Terms.html | webpage | Web page needs to be polished | Minor |  | Aaron and Cristian
12 | Ravindu Gunasinghe | Terms.html | file | The code is still heavily disorganized and messy. | Minor |  | Mohammed and Cristian
13 | Ravindu Gunasinghe | SignUp.html | 29-30 | Let user know that the email has bee taken or not. Add javascript function. | Minor |  | Ravindu
14 | Talha Harooni | Homepage |  | I think it was overall good, I didn't find any defects, maybe more work in the future to improve it. | Minor |  | Vince and Ravindu
15 | Talha Harooni | Account |  | Needs more styling | Minor |  | Talha
16 | Talha Harooni | Terms |  | Messy needs to be reorganized, but see improvement. | Minor |  | Cristian and Mohammed
Note on A1: This is a sequential number that gives a reviewer's comments a unique ID for ease of referencing.
Note on B1: Enter your name.
Note on C1: For documents with multiple pages, enter the page number or numbers for the defect or comment. For example: ii, 12, 4-5
Note on D1: Enter the identifying number or title for the Section, Paragraph, Figure, or Table for which you are entering a defect or comment. For examples: 4.6.2, Stakeholder Plan.
Note on E1: Enter a detailed description of the defect you are identifying or provide your detailed comment. Identify only one defect or comment per row.
Note on F1: This column is automatically populated based on the entry chosen in the Defect/Comment Type column.
Note on G1: This column is used to assign a disposition to the review comment.
Note on H1: This column is used for identifying the person assigned to resolve the defect/comment.
Note on I1: This column is used to record freeform notes about each defect and or its disposition.